## Sheet1
Estimated Time Remaining
User Story | Tasks | In Charge | Estimate | Day 1 | Day 2 | Day 3 | Day 4
As a user, I would like to register an account with PinG! | Create MySQL Database Schema | Richard and Zach | 1 hour | 0 hours |  |  |  | ✓
| Create tables to store user profiles. | Richard and Zach | 1 hour | 0 hours |  |  |  | ✓
| Create stored procedure for inserting user to DB. | Richard and Zach | 1 hour | 0 hours |  |  |  | ✓
| Deriving a way to interact with stored procedures. | Monica and Juan | 3 hours | 2 hours
| Create a simple UI (IOS) | Koji and Jordan | 3 hours | 3 hours | 2 hours
| Create a simple UI (Android) | Arthur and Jorge | 3 hours | 2 hours
| Add touch and create event functionality (IOS) | Koji and Jordan | 4 hours | 3 hours
| Add touch and create event functionality (Android) | Arthur and Jorge
Estimated Time Remaining
User Story | Tasks | In Charge | Estimate | Day 1 | Day 2 | Day 3 | Day 4
As a user, I want to be able to create an event so other people can see it | Create tables to store events. | Richard and Zach | 1 hour | 0 hours |  |  |  | ✓
| Create stored procedure for inserting events into DB. | Richard and Zach | 1 hour | 0 hours |  |  |  | ✓
| Deriving a way to interact with stored procedures. | Monica and Juan | 3 hours | 2 hours
| Connect the app interface to Google Maps API (IOS) | Koji and Jordan | 4 hours | 2 hours
| Connect the app interface to Google Maps API (Android) | Arthur and Jorge
| Create a simple UI (IOS) | Koji and Jordan | 2 hours | 1 hours
| Create a simple UI (Android) | Arthur and Jorge | 3 hours | 2 hours
| Add touch and create event functionality (IOS) | Koji and Jordan | 4 hours | 4 hours
| Add touch and create event functionality (Android) | Arthur and Jorge
Estimated Time Remaining
User Story | Tasks | In Charge | Estimate | Day 1 | Day 2 | Day 3 | Day 4
As a user, I want to be able to see events on my vicinity | Create stored procedure for querying events in DB. | Richard and Zach | 1 hour
| Deriving a way to interact with stored procedures. | Monica and Juan | 3 hours | 2 hours
| Refreshing events on the map (IOS) | Koji and Jordan | 3 hours | 3 hours
| Refreshing events on the map (Android) | Arthur and Jorge | 3 hours | 2 hours